## Sheet1
WeChat-Mobile2.0 schedule
module | items | time | operator | fromDate | toDate | UI | shangxueyun | items | toDate | fromDate | progress | Remark
login | presession | 1week | wangle | 2017-02-20 | 2017-02-20 | 1week | shangxueyun | login UI | 2017-02-21 | 2017-02-21 | complete
| authenticate |  | wangle | 2017-02-21 | 2017-02-21 |  | shangxueyun | authenticate call test | 2017-02-22 | 2017-02-22 | complete
| 2fa |  | wangle | 2017-02-22 | 2017-02-24 |  | shangxueyun | 2fa UI | 2017-02-23 | 2017-02-23 | complete
|  |  | wangle |  |  |  | shangxueyun | 2fa call test | 2017-02-24 | 2017-02-24 | complete
watchlist | pmp setting | 2week |  | 2017-02-27 | 2017-02-28 | 2week | shangxueyun | watchlist Thinking structure build | 2017-02-27 | 2017-02-27 | complete
| names |  |  | 2017-02-28 | 2017-03-01 |  | shangxueyun | watchlist UI menus and title name | 2017-02-28 | 2017-03-01 | complete
| detail |  |  | 2017-03-01 | 2017-03-02 |  | shangxueyun | watchlist Id and name API test Fill UI | 2017-03-01 | 2017-03-03 | complete
| add |  |  | 2017-03-03 | 2017-03-03 |  | shangxueyun | watchlist detail UI | 2017-03-06 | 2017-03-06 | complete
| remove |  |  | 2017-03-06 | 2017-03-10 |  | shangxueyun | watchlist detail API test Fill UI | 2017-03-07 | 2017-03-08 | complete
[7 empty] | shangxueyun | watchlist Transverse longitudinal scroll | 2017-03-07 | 2017-03-08 | complete
[7 empty] | shangxueyun | watchlist Contract Subscribe update |  |  | complete
[7 empty] | shangxueyun | Watchlist Add UI |  |  | complete
[7 empty] | shangxueyun | watchlist Add all function API test Fill UI realization |  |  | complete
[7 empty] | shangxueyun | Watchlist Remove UI |  |  | complete
[7 empty] | shangxueyun | watchlist Remove all function API test Fill UI realization | 2017-03-08 | 2017-03-09 | complete
Order | today | 1week |  | 2017-03-13 | 2017-03-14 | 1week | shangxueyun | Order Thinking structure build | 2017-03-09 | 2017-03-10 | complete
| history |  |  | 2017-03-15 | 2017-03-16 |  | shangxueyun | Order UI | 2017-03-13 | 2017-03-13 | complete
|  |  |  | 2017-03-16 | 2017-03-17 |  | shangxueyun | Order today UI |  |  | complete
[7 empty] | shangxueyun | Order History UI and select |  |  | complete
[7 empty] | shangxueyun | Order today UI API test Fill UI |  |  | complete
[7 empty] | shangxueyun | Order History UI and select API test Fill UI |  |  | complete
[7 empty] | shangxueyun | today and History ST Order detail UI |  |  | complete
[7 empty] | shangxueyun | today and History ST Order detail API test Fill UI |  |  | complete
[7 empty] | shangxueyun | today and History CFD Order detail UI |  |  | complete
[7 empty] | shangxueyun | today and History CFD Order detail API test Fill UI |  |  | complete
[7 empty] | shangxueyun | today and History FT/FX/FXMN Order detail UI |  |  | complete
[8 empty] | today and History FT/FX/FXMN Order detail API test Fill UI |  |  | complete
[8 empty] | today and History UT Order detail UI |  |  | complete
[7 empty] | shangxueyun | today and History UT Order detail API test Fill UI |  |  | complete
[7 empty] | shangxueyun | ST Order Withdraw and Amend UI |  |  | complete
[7 empty] | shangxueyun | ST Order Withdraw and Amend function API test Fill UI |  |  | complete
[7 empty] | shangxueyun | CFD Order Withdraw and Amend UI |  |  | complete
[7 empty] | shangxueyun | CFD Order Withdraw and Amend function API test Fill UI |  |  | complete | 目前没有cfd的修改API
[7 empty] | shangxueyun | FT/FX/FXMN Order Withdraw and Amend UI |  |  | complete
[7 empty] | shangxueyun | FT/FX/FXMN Order Withdraw and Amend function API test Fill UI |  |  | complete
[7 empty] | shangxueyun | UT Order Withdraw UI |  |  | complete
[7 empty] | shangxueyun | UT Order Withdraw function API test Fill UI |  |  | complete
portfoliocontent | content | 1week |  | 2017-03-20 | 2017-03-22 | 1week | shangxueyun | portfolio Thinking structure build |  |  | complete
| detail |  |  | 2017-03-23 | 2017-03-24 |  | shangxueyun | portfolio UI data API test Fill |  |  | complete
[7 empty] | shangxueyun | portfolio ST detail UI |  |  | complete
[7 empty] | shangxueyun | portfolio ST detail data API test Fill |  |  | complete
[7 empty] | shangxueyun | portfolio CFD detail UI
[7 empty] | shangxueyun | portfolio CFD detail data API test Fill |  |  | complete
[7 empty] | shangxueyun | portfolio FT/FX/FXMN detail UI |  |  | complete
[7 empty] | shangxueyun | portfolio FT/FX/FXMN detail data API test Fill |  |  | complete | 部分API UI无法实现 如FT/FX/FXMN没API UT空数据
outstanding position | content | 1week |  | 2017-03-27 | 2017-03-28 | 1week | shangxueyun | outstanding position Thinking structure build |  |  | complete
|  |  |  | 2017-03-29 | 2017-03-29 |  | shangxueyun | outstanding position UI |  |  | complete
[7 empty] | shangxueyun | outstanding position data API test |  |  | complete
[7 empty] | shangxueyun | outstanding position EQ detail UI |  |  | complete
[7 empty] | shangxueyun | outstanding position EQ detail API test |  |  | complete
[7 empty] | shangxueyun |  |  |  | complete
[8 empty] | outstanding position UT detail API test |  |  | complete | EQ目前没数据and数据不全，UI显示为-，UT没数据暂无UI
trade | detail | 2week |  | 2017-04-03 | 2017-04-04 | 1week | shangxueyun | watchlist ST order UI |  |  | complete
| search |  |  | 2017-04-05 | 2017-04-05 |  | shangxueyun | watchlist ST order API test |  |  | complete
| amend |  |  | 2017-04-06 | 2017-04-07 |  | shangxueyun | watchlist ST order data Fill UI |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [Limited Order] |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [Limited Order] order function |  |  | complete
| withdraw | [5 empty] | shangxueyun | watchlist CFD [Stop Limited Order] |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [Stop Limited Order] order function |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [Trailling Stop Order] |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [Trailling Stop Order] order function |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [OCO Order] |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [OCO Order] order function |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [Contingency Order] |  |  | complete
[7 empty] | shangxueyun | watchlist CFD [Contingency Order] order function |  |  | complete
[11 empty] | complete | FT/FX/FXMN 三个类型
[7 empty] | shangxueyun | watchlist FT/FX/FXMN [Limit][Stop on bid][Stop on offer] |  |  | complete
[7 empty] | shangxueyun | watchlist FT/FX/FXMN [Limit][Stop on bid][Stop on offer] order function |  |  | complete
[7 empty] | shangxueyun | watchlist FT/FX/FXMN [Stop Limit] |  |  | complete
[7 empty] | shangxueyun | watchlist FT/FX/FXMN [Stop Limit] order function |  |  | complete
[7 empty] | shangxueyun | watchlist FT/FX/FXMN [OCO Stop on bid][OCO Stop on offer] |  |  | complete
[7 empty] | shangxueyun | watchlist FT/FX/FXMN [OCO Stop on bid][OCO Stop on offer] order function |  |  | complete
complete
[7 empty] | shangxueyun | watchlist UT order UI |  |  | complete
[7 empty] | shangxueyun | watchlist UT order function API test Fill UI |  |  | complete
trade Search | SearchCounter | [5 empty] | shangxueyun | Trade Search UI |  |  | complete
[7 empty] | shangxueyun | Search function and class select |  |  | complete
[7 empty] | shangxueyun | Search detail UI |  |  | complete
[7 empty] | shangxueyun | Search detail data and select data |  |  | complete
[7 empty] | shangxueyun | Trade Search History UI |  |  | complete
[7 empty] | shangxueyun | Search History local data storage mechanism |  |  | complete
[7 empty] | shangxueyun | Search History Again data Fill UI |  |  | complete | 目前数据存储做到，只限制一个设备每次保存的Search数据
test |  | 1week |  | 2017-04-10 | 2017-04-14 | 1week
[8 empty] | 1.Portfolio product calculation adjustment.（status：ok） |  |  | complete
|  | 1.Watchlist FX/FXMN Subscribe Spreads data adjustment | [5 empty] | 2.inspect watchlist FT/FX/FXMN subscription data.(status:Invalid product) |  |  | complete
|  | 2.login error message returned handle | [5 empty] | 3.Trade Stocks and Trade CFD LimitBalance data（status：Have in hand） |  |  | complete
|  | 3.add tradeEnable trade limit | [5 empty] | 4.Watchlist FT/FX/FXMN/NFX cannot get pmpTopic . |  |  | complete
|  | 4.trade submit order repeat invalid order | [5 empty] | 5.Watchlist remove API data transfer parameter problem. |  |  | complete
|  | 5.trade order and cancel/amend passwordConfirmation need input | [5 empty] | 6.Add UT module subscription data. |  |  | complete
[8 empty] | 1.Watchlist data refresh.(status:ok) 2.Watchlist data later 0 clear.(status:ok) 3.Trading input password issue.(status:ok) 4.Subscription data shows the undefined problem. |  |  | complete
|  | 6.order submit parameter optimization unified | [8 empty] | complete
|  | 7.order cancel/amend optimization unified UI adjustment | [8 empty] | complete
|  | 8.Study .net | [8 empty] | complete
1.login add use hints
2.Study .net